## Photographer + user
| Mockups link | https://xd.adobe.com/view/91f4246b-3736-4d72-a1d7-30789634f90d-c4a7/screen/41b5a682-206e-465c-aaea-ee4eefca0d87/
|  | Features | Required Days
Photographer
|  | Instamojo payment integration | 4 | Link integration | Post launch
|  | Chat Filter | 1.5 | Done
|  | Signup form (skills + other steps) | 1 | Done
|  | Photographer portfolio API+design+functionality + integration on user side | 3 | Done
|  | Booking timeline management + design + dropbox link management+ APIs | 3 | Done
|  | SOS + Flipsnack integration | 6 |  | Post launch
|  | Equipments & gear + APIs + design | 1 | Done
User side
|  | Photographer profile details handling | 1 | Done
|  | Add booking UI + functionality + APIs | 3 | Done
|  | Reschedule booking handling + APIs + design + rating | 2 | Done
|  | Photographer portfolio + APIs | 1 | Done
|  | Testing + Modifying + publishing | 5
|  | IOS testing + errors handling + release | 5
|  | Total Days required | 36.5
Include extra 3 4 days incase of emergency